## Sheet1
Portfolio | Cluster Group | Cluster | Request# | Urgency | Status | Enviornment | Application (Or Assignment Group) | Request Description | Category | Sub-Category | Effort Bucket | Open Date | Open Year | Open Period | Open Week | Open Period # | Business Need By Date | BIS Committed Date | Estimated Effort (Hrs) | Actual Effort (Hrs) | Assigned Date | Assigned Year | Assigned Period | Assigned Week | Acknowledged Date | Acknowledged Year | Acknowledged Period | Acknowledged Week | Resolved Date | Resolved Year | Resolved Period | Resolved Week | Resolved Period # | # Of Issues Reported | Response SLA Exception? | Eligible For AMR Count for Response SLA? | Met Response Time SLA? | Schedule SLA Exception? | Eligible For AMR Count for Schedule SLA? | Met Schedule Adherence SLA? | Release Involved? | Release Type | Release Priority | RFC# | Total Issues # | RM Issues # | Non-RM Issues # | Reoccurring / Non-Reoccurring | Comments (Mandatory if marked as SLA exception)
FLNA | Finance | Track1 | Q243987 | Medium | Resolved | Production | AOP | Item File inquiry in CAP | Routine Maintenance | User Assistance | LE20 | 2012-06-11 | 2012 | P6 | W4 |  |  | 2012-06-19 |  |  | 2012-06-11 | 2012 | P6 | W4 | 2012-06-11 | 2012 | P6 | W4 | 2012-06-19 | 2012 | P7 | W1 |  | 0 | No | 1 | 1 | No | 1 | 1 | No |  |  |  | 0 | 0 | 0
FLNA | Finance | Track1 | 362944 | Medium | Resolved | Production | AMP | ML-Change Claim Status for FSV claims on APEX feed | Corrective Maintenance | User Assistance | LE10 | 2012-07-09 | 2012 | P7 | W4 |  |  | 2012-07-16 |  |  | 2012-07-09 | 2012 | P7 | W4 | 2012-07-09 | 2012 | P7 | W4 | 2012-07-16 | 2012 | P8 | W1 |  | 0 | No | 1 | 1 | No | 1 | 1 | No | No |  |  | 0 | 0 | 0
FLNA | Finance | Track1 | 364065 | Medium | Resolved | Production | FC2 | Stop printing the physical copy of the Final SER (Filtered) report bty Period 10, 2012 | User Support | Business | LE10 | 2012-08-03 | 2012 | P8 | W3 |  |  | 2012-12-05 |  |  | 2012-08-03 | 2012 | P8 | W3 | 2012-08-03 | 2012 | P8 | W3 | 2012-12-05 | 2012 | P13 | W1 |  | 0 | No | 1 | 1 | No | 1 | 1 | No | No |  |  | 0 | 0 | 0
FLNA | Finance | Track1 | 364056 | Medium | Resolved | Production | FC2 | Changes to FC2 Prelim Cycle to accomodate Frito Lay Holidays | Routine Maintenance | Ad-hoc/Special/Exception/Holiday Runs/Schedules | LE10 | 2012-08-03 | 2012 | P8 | W3 |  |  | 2012-12-05 |  |  | 2012-08-03 | 2012 | P8 | W3 | 2012-08-03 | 2012 | P8 | W3 | 2012-12-05 | 2012 | P13 | W1 |  | 0 | No | 1 | 1 | No | 1 | 1 | Yes | Yes | Standard | 29948 | 0 | 0 | 0
FLNA | Finance | Track1 | 363860 | Medium | Open | Production | FS2,FC2 | ACH Items which hit the customer bank account should include ticket number. | User Support | Business |  | 2012-07-31 | 2012 | P8 | W3
FLNA | Finance | Track1 | 363852 | Medium | In-Progress | Production | FS2,FC2 | Cash Deposit Coupon Project | User Support | Business |  | 2012-07-31 | 2012 | P8 | W3 | [5 empty] | 2012-07-31 | 2012 | P8 | W3 | 2012-07-31 | 2012 | P8 | W3
FLNA | Finance | Track1 | 363837 | Medium | Open | Production | FC2 | Report of all routes contained in the combined report. | User Support | Business |  | 2012-07-31 | 2012 | P8 | W3
Note on D1: Author: SD # in SM7
Note on E1: Author: Urgency in SM7
Note on H1: Author: Assignment Group in SM7 and Project Name in Star team
Note on I1: Author: Description in SM7
Note on J1: Author: Preventive,Adaptive,Routine Maintenance,Business Support